## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 1/27 - 2/16 | Established norms for epics vs. labels in PivotalTracker Divvied up roles and responsibilities Decided tech stack Decided DevOps tools Decided hosting environment Established scope of initial project phase | None yet | Varying levels of technical expertise on the team, including with use of ReactJS and Django. Need to assign stories to developers based on story complexity. | Need to come up with clearer assignment of tasks and communication of team deadlines given varying schedules amongst engineers. | 0 | 35 in icebox for essential/desirable | 0 | 0 | 0 | 150.5 | 172 | 8 | 47.5 | 22 | 4 | 2 | 3 | 36.5 | 14.5 | 7.5
1
2
3

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## George
Lead Roles: Team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 6 | 6 | 1.5 | 0 - Learn PivotalTracker best practices 1 - plan high level requirements with team 2 - weigh SQL/noSQL approaches 4 - discuss best QA approach with team 5 - run team meetings, remind of deliverables 6 - work with Zach to establish DevOps policies with team | 1 | 1 | 0.5 | 0 | 1 | 2 | 0.5 | 0 | Established group communication standards, project scope, roles and responsibilities, housekeeping items | None yet | Need to incorporate Aysha to team as Security Leader and get her up to speed on project scope | Need to establish policy for branching | 3
2 | 2/3-2/9 | 4.5 | 10.5 | 2 | 0 - none 1 - Input a few test stories to Pivotal, solidify scope with team 2 - none 3 - none yet 4 - continue to discuss QA procedures with team 5 - run team meetings, start SPPP doc with team 6 - work with Zach to solidify DevOps practices | 0 | 0.5 | 0 | 0 | 0.5 | 3 | 0.5 | 0 | Start of SPPP | None yet | None yet | iter0 deliverables | 5
3 | 2/10-2/16 | 10.5 | 21 | 5 | 0 - none 1 - entered all "optional" requirements in Pivotal 2 - none 3 - none yet 4 - none yet 5 - ran meetings, worked on iter0 deliverables 6 - established CI/CD pipeline policies with Zach 7 - none | 0 | 2 | 0 | 0 | 0 | 8 | 0.5 | 0 | SPPP sections, iter0 PowerPoint slides | None yet | None yet | Divvy up stories for initial implementation, collaborate on design doc, refine Pivotal | 20

## Vibhu
Lead Roles: Backup Team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 5 | 5 | 1.5 | 0 - Revisit basics of Django, React 2 - Researched and Suggested the pros of using noSQL over SQL based db 4 - Discussed inclusion of Basic unit tests for checking backend Featues 5 - Help inorganizing meetings, setting up agenda, provide an expert opinion | 2 | 0 | 0.5 | 0 | 0.5 | 2 | 0 | 0 | set up git, formalized the working of project, selected tech stack. | None | None | research on deploying frontend-backend combined | 2
2 | 2/3-2/9 | 5 | 10 | 2 | 1 - Researched and discussed use of docker for unifying build process. 2 - Explored more on the development of MVP and functionalities of the product 5 - Basic logistic stuff and setting up meetings | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 0 | Create an in-depth product functionality doc, work on SPPP document | None | None | Set up pivotal tracker, iter 0 deliverables | 2
3 | 2/10-2/16 | 7.5 | 17.5 | 4 | 0 - Learnt basics of Pivotal tracker 1 - Filled out user stories for pivotal tracker and completed deliverables for iter - 0 3 - Researched on setting up standards for documentation, code-style, pull-request and bugs 5 - Assisted in meetings and basic check-up | 0.5 | 2 | 0 | 1 | 0 | 4 | 0 | 0 | set up github and code standards, Pivotal tracker, iter-0 presentation | None | None | work on wireframes, start implementing functionality, Learn more about unit-tests | 5

## Karen
Role | Requirement and design leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 01/27-02/02 | 7.5 | 6 | 1.5 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Set up git, commit a test message on git | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 03/02-9/02 | 7 | 5 | 2 | 0 - learn django, read several tutorials 1 - create user stories 5 - review lab2 and iteration#0 6 - set up django | 1.5 | 1.5 |  |  |  | 1.5 | 0.5 |  | None | 1. Need to keep working with django and react | 5- Some points arent very clear, emailed the professor | Continue to learn Django and define requirements and tasks Reasearch about design and review the tutorial made by Zach Finish section in SPP and lab2 | 8
3 | 02/10-02/17 | 12 | 7 | 5 | 0 - Learn Pivotaltracker 1 - Enter the user stories related to managing a private event 5 - Finish section in SPP and lab2 | 0.5 | 3 |  |  |  | 3.5 |  |  | Section of functional requiremnts( SPP docuemnt and presentation), and style of the document | None | None | Review design patterns and start with SDD document, assist in any technical work that may begin | 8

## Chris
Role: Requirements Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 6 | 4.5 | 1.5 | 0 - validated git connection and read up on/experimented with GitHub Desktop 2 - reviewed initial project conecpt per original documentation I created prior to this class beginning | 3 |  | 1.5
2 | 2/3-2/9 | 10 | 5 | 2 | 0 - learn Pivotal Tracker 6 - Joined POC call where Zach developed the foundational pieces of React/Django | 5 | [5 empty] | 3 |  | 1 - Created Pivotal tracker example stories
3 | 2/10-2/16 | 12.5 | 8 | 4.5 | 0 - Researching SPPP, Competitive/Related product analysis 7 - research similar products, added to SPPP, created competitor table | 3 | [6 empty] | 5 | 7 - SPPP related products segment |  |  | Integrate stories as a team, begin coding stories assigned, will have to learn about Django framework, python unit testing, and working in Python IDE

## Zach
Role: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 6 | 6 | 3.5 | 0 - learn to connect react and django together 6 - create two proof of concepts, one using React/Django, one using Django 7 - Zoom call with Chris and Matt so they can watch how the POC setup works | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 0 (2) | Created two pocs so group could decide on tech stack | N/A |  | Setting up CI in Github | 6
2 | 2/3-2/9 | 6 | 12 | 2 | 0 - learn Github Actions and CI/CD, research best actions to use 6 - Implement Github actions for CI | 3 | 0 | 0 | 0 | 0 | 0 | 3 |  | Started work on SPPP | N/A |  | Deploying to Heroku, working on SPPP | 6
3 | 2/10-2/16 | 7 | 19 | 5 | 0 - learn how to deploy django/react projects to Heroku 1 - work on SPPP and Pivotal Tracker 6 - set up main to depoy to Heroku, | 3 | 2 | 0 | 0 | 0 | 0 | 2 |  | Worked on SPPP and Pivotal Tracker requirements | N/A |  | Adding linters to CI process, documenting development branch, setting up Mongo, wireframes | 15

## Matthew
Role: Quality Assurance Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 01/27-02/02 | 9 | 5.5 | 3.5 | Individual Task Breakdown 0 - Relearned Git, Watched Zach build both the django/react and react poc's, watched tutorials on both django and react 1 - plan future requirements 4 - discuss QA processes 5 - communication with team about project setup and my specific role 6 - set up Git/Git Desktop | 4 | 1 | 0.5 | 0 | 1 | 2 | 0.5 | 0 | establish group role, set up Github | unfamiliarity with django and react | rewatch poc builds, go through tutorials | continue learning framework, look into pivotal, learning QA roles | 6
2 | 03/02-9/02 | 6 | 4 | 2 | Individual Task Breakdown 0 - perform coding tutorials in both django and react/rewatch Zach's poc video 1 - explore pivotal, read up on pivotal 5 - begin SPPP doc / review lab 2 | 4 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | set up pivotal tracker, start SPPP | unfamiliarity with pivotal | read pivotal tutorials | add pivotal stories, finish SPPP, contribute to iter0 ppt | 12
3 | 02/10-02/17 | 11 | 6 | 5 | Individual Task Breakdown 0 - review tutorials on QA processing 1 - worked on adding stories to pivotal and finishing SPPP 3 - implementation 5 - communication with group on pivotal/SPPP/iter0 ppt | 3 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | finish SPPP, finish iter0 ppt, finish pivotal stories | QA proccesses unfamiliarity | read up on QA development and implementation | assist in any technical work that may begin, try to get ahead of learning frameworks as the develop, learn more QA processes set up QA tracking | 12

## Aysha
Role: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 01/27-02/02 | 5 | 6 | 1 | Individual Task Breakdown 0 - Refreshed Git,Watched Zach tutorial on Django 5 - communicated with team members on my role 6 - set up git 7 - research on security related functions | 3 |  |  |  |  | 1 | 1 | 2 | 1. Completed Lab 1 | 1. No previous experience with Django 2. My individual contribution to the task not clear | 1. Talk with Karen to get in track 2. Work on my contributtion to the team | Meet Karen | 6
2 | 03/02-9/02 | 7 | 8 | 1 | Individual Task Breakdown 0 - DJango, Rest API for Django 1 - Work on user stories 3 - Creater User stories and assigned points 5 - Communicated with Karen and worked on pending task | 4 | 1 |  | 1 |  | 2 |  |  | 1. Completed Lab 2 | 1. Need to work more on programming in Django 2. My individual contribution to the task is still a work in progress | 1. Talk with Karen to get in track 2. Work on my contributtion to the team | Meet Karen | 7
3 | 02/10-02/17 | 10 | 11 | 5 | Individual Task Breakdown 0 - Research on non functional requirments 1 - Worked on user stories 3 - completed SPPP and presentation 5 - Communicated with Team and decided on the presentation | 2 | 2 |  | 3 |  | 5 |  |  | 1. Completed SPPP and presentation | 1. Worked on security protocols | None 2. Work on my contributtion to the team | Make sure lab2 is done properly | 10