## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 1/27 - 2/16 | Established norms for epics vs. labels in PivotalTracker Divvied up roles and responsibilities Decided tech stack Decided DevOps tools Decided hosting environment Established scope of initial project phase | None yet | Varying levels of technical expertise on the team, including with use of ReactJS and Django. Need to assign stories to developers based on story complexity. | Need to come up with clearer assignment of tasks and communication of team deadlines given varying schedules amongst engineers. | 0 | 35 in icebox for essential/desirable | 0 | 0 | 0 | 189.5 | 134 | 8 | 47.5 | 22 | 4 | 2 | 3 | 33.5 | 14.5 | 7.5
1 | 2/17 - 3/9 | Implemented initial UI using react-bootstrap User registration User login Basic CRUD operations on a record type in database End to end connectivity with database |  | Limited test coverage thus far |  | 0 | 10pts in current iteration, 7 pts just awaiting testing | 0 | 0 | 0 | 214.5 | 153 | 8 | 45 | 25 | 8 | 18 | 0.5 | 38 | 10.5 | 8
2
3

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## George
Lead Roles: Team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 7.5 | 6 | 1.5 | 0 - Learn PivotalTracker best practices 1 - plan high level requirements with team 2 - weigh SQL/noSQL approaches 4 - discuss best QA approach with team 5 - run team meetings, remind of deliverables 6 - work with Zach to establish DevOps policies with team | 1 | 1 | 0.5 | 0 | 1 | 2 | 0.5 | 0 | Established group communication standards, project scope, roles and responsibilities, housekeeping items | None yet | Need to incorporate Aysha to team as Security Leader and get her up to speed on project scope | Need to establish policy for branching | 3
2 | 2/3-2/9 | 6.5 | 4.5 | 2 | 0 - none 1 - Input a few test stories to Pivotal, solidify scope with team 2 - none 3 - none yet 4 - continue to discuss QA procedures with team 5 - run team meetings, start SPPP doc with team 6 - work with Zach to solidify DevOps practices | 0 | 0.5 | 0 | 0 | 0.5 | 3 | 0.5 | 0 | Start of SPPP | None yet | None yet | iter0 deliverables | 5
3 | 2/10-2/16 | 15.5 | 10.5 | 5 | 0 - none 1 - entered all "optional" requirements in Pivotal 2 - none 3 - none yet 4 - none yet 5 - ran meetings, worked on iter0 deliverables 6 - established CI/CD pipeline policies with Zach 7 - none | 0 | 2 | 0 | 0 | 0 | 8 | 0.5 | 0 | SPPP sections, iter0 PowerPoint slides | None yet | None yet | Divvy up stories for initial implementation, collaborate on design doc, refine Pivotal | 20
4 | 2/17-2/23 | 7 | 5 | 2 | 0 - long discussion of OAuth in weekly group meeting 1 - refined stories with group for week 1 of iteration 1, decided scope for upcoming week. 2 - Initial design discussion with Karen during weekly meeting 3 - none outside of disussion during weekly meeting 4 - none 5 - lead weekly group meeting, side discussions with all members 6 - none 7 - none | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | Updated meeting minutes, divvied up SDD document per section | Need to establish security mechanism front- vs back-end. | Aysha/Vibhu/Chris to determine architecture | Work with Matt on end-to-end test management. | 2
5 | 2/24-3/2 | 3 | 1 | 2 | 1 - reviewed stories on pivotal 5 - hosted team meeting | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
6 | 3/3-3/9 | 18 | 12 | 6 | 0 - rewatched Zach workshop from previous week, attended current workshop 1 - fixed pivotal stories to revert to django-managed auth 2 - built wireframes in whimsical 3 - none 4 - fixed test cases on Pivotal for switch away from google auth 5 - ran group meeting, updated deliverables 6 - set up local environment, worked on getting Selenium up and running 7 - none | 2 | 1 | 1 | 0 | 1 | 4 | 3 | 0 | Created wireframes, updated SPPP, proofread SDD, added intro slides to presentation, checked progress report for adherence to required formulas | Unable to get Selenium up and running yet | Work with Matt to resolve | Selenium up, first few automated tests written and working | 5

## Vibhu
Lead Roles: Backup Team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 6.5 | 5 | 1.5 | 0 - Revisit basics of Django, React 2 - Researched and Suggested the pros of using noSQL over SQL based db 4 - Discussed inclusion of Basic unit tests for checking backend Featues 5 - Help inorganizing meetings, setting up agenda, provide an expert opinion | 2 | 0 | 0.5 | 0 | 0.5 | 2 | 0 | 0 | set up git, formalized the working of project, selected tech stack. | None | None | research on deploying frontend-backend combined | 2
2 | 2/3-2/9 | 7 | 5 | 2 | 1 - Researched and discussed use of docker for unifying build process. 2 - Explored more on the development of MVP and functionalities of the product 5 - Basic logistic stuff and setting up meetings | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 0 | Create an in-depth product functionality doc, work on SPPP document | None | None | Set up pivotal tracker, iter 0 deliverables | 2
3 | 2/10-2/16 | 8.5 | 4.5 | 4 | 0 - Learnt basics of Pivotal tracker 1 - Filled out user stories for pivotal tracker and completed deliverables for iter - 0 3 - Researched on setting up standards for documentation, code-style, pull-request and bugs 5 - Assisted in meetings and basic check-up | 0.5 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | set up github and code standards, Pivotal tracker, iter-0 presentation | None | None | work on wireframes, start implementing functionality, Learn more about unit-tests | 5
4 | 2/17 - 2/23 | 6.5 | 4.5 | 2 | 0 - Learnt about docker, discussion about oAuth. 1 - Added user acceptance tests and modified stories on pivotal tracker. 2 - Set up Class diagrams for my user stories. 5 - Assisted in weekly meetings. | 1.5 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | None | None | None | Zack is supposed to do majority of the work so just checking up with the group | 1
5 | 2/24 - 3/2 | 5 | 3 | 2 | 0 - Setup repository environment and test login/signup 1 - know more about DB and Classes section of SDD 5 - Basic Meeting logistics | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Setup app environment, thought about DB classes and the functions for user story. | None | None | Set up automatic API, Work with chris to create this week's user stories, Learn django-rest-framework. | 6
6 | 3/3 - 3/9 | 13 | 8.5 | 4.5 | 0 - Learnt about react.js, django-rest-framework, djongo. 1 - Set up automatic API for front end and backend and completed deliverables for iteration-1 2 - Used Karen's diagrams to construct database models. 3- Pair programming with chris to help him setup the event class 5- Assisted in daily meetings, organized logistics. | 2 | 2 | 1 | 2 | 0 | 1.5 | 0 | 0 | Added jsdoc support to document code in frontend, completed SDD document, Iteration-1 presentation | None | None | Help with anything chris or zack need completion in. Add pdoc documentation code for python backend. | 3

## Karen
Role | Requirement and design leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 01/27-02/02 | 7.5 | 6 | 1.5 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Set up git, commit a test message on git | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 03/02-9/02 | 7 | 5 | 2 | 0 - learn django, read several tutorials 1 - create user stories 5 - review lab2 and iteration#0 6 - set up django | 1.5 | 1.5 |  |  |  | 1.5 | 0.5 |  | None | 1. Need to keep working with django and react | 5- Some points arent very clear, emailed the professor | Continue to learn Django and define requirements and tasks Reasearch about design and review the tutorial made by Zach Finish section in SPP and lab2 | 8
3 | 02/10-02/17 | 12 | 7 | 5 | 0 - Learn Pivotaltracker 1 - Enter the user stories related to managing a private event 5 - Finish section in SPP and lab2 | 0.5 | 3 |  |  |  | 3.5 |  |  | Section of functional requiremnts( SPP docuemnt and presentation), and style of the document | None | None | Review design patterns and start with SDD document, assist in any technical work that may begin | 8
4 | 2/17-2/23 | 9.5 | 7 | 2.5 | 0 - Learn modeling React class 2 - software architecture and class diagram SDD | 3 |  | 4 | [5 empty] | Software architure , and part of class diagram | Definition of some classes | Review with team , we all found the solution | Fix and finish sections, set up project in my computer | 8
5 | 2/24-3/2 | 7 | 5 | 2 | 2 - changes in the diagrams 6- set all configuratio |  |  | 3 |  |  |  | 2 |  | Software architure, class diagram and patterns | None | None
6 | 3/3-3/9 | 11 | 5 | 6 | 0 - rewatched Zach workshop from previous week 2 - set pptx slides and orginize SDD section document | 2 |  |  |  | 3 |  |  |  | Software architure, class diagram and patterns | None | None | Start developing some stories and star reviewn the next deliverable. | 6

## Zach
Role: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 9.5 | 6 | 3.5 | 0 - learn to connect react and django together 6 - create two proof of concepts, one using React/Django, one using Django 7 - Zoom call with Chris and Matt so they can watch how the POC setup works | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 0 (2) | Created two pocs so group could decide on tech stack | N/A |  | Setting up CI in Github | 6
2 | 2/3-2/9 | 8 | 6 | 2 | 0 - learn Github Actions and CI/CD, research best actions to use 6 - Implement Github actions for CI 7- workshop: log in with google | 3 | 0 | 0 | 0 | 0 | 0 | 3 |  | Started work on SPPP | N/A |  | Deploying to Heroku, working on SPPP | 6
3 | 2/10-2/16 | 12 | 7 | 5 | 0 - learn how to deploy django/react projects to Heroku 1 - work on SPPP and Pivotal Tracker 6 - set up main to depoy to Heroku, | 3 | 2 | 0 | 0 | 0 | 0 | 2 |  | Worked on SPPP and Pivotal Tracker requirements | N/A |  | Adding linters to CI process, documenting development branch, setting up Mongo, wireframes | 15
4 | 2/17-2/23 | 20 | 18 | 2 | 0 - learn how to use google ouath 3 - work on log in, sign up stories 6 - reconfigure local django database 7 -workshop: log in with google | 4 | 0 | 0 | 10 | 0 | 0 | 1 | 3 | Setup oauth and user log in and sign up | N/A
5 | 2/24-3/2 | 23 | 21 | 2 | 0 - learn how to connect mongodb to django backend 1 - work on security analysis on SDD 3 - work on log in, sign up stories 6 - switch project database to MongoDb 7 - workshop: react overview | 2 | 0 | 0 | 14 | 0 | 0 | 3 | 2 | Switched database to mongodb, set up development heroku server | Ouath proving difficult to manage
6 | 3/3-3/9 | 19 | 14 | 5 | 0 - learn how to implement jwt with django 1 - SDD work 3 - redo authentication and log/logout stories, added preliminary ui/ux 6 - workshop: react overview part 2 | 3 | 1 | 0 | 8 | 0 | 0 | 0 | 2 | -Reconfigured app authentication to use jwt and django's built in User model -Implemented ui design from wireframes to available components | N/A |  | Work on CRUD for Events and tying them to users | 15
7 | 3/10-3/16 |  |  |  | 0 - 1 - 3 - 6 -
8 | 3/17-3/23 |  |  |  | 0 - 1 - 3 - 6 -
9 | 3/24-3/30 |  |  |  | 0 - 1 - 3 - 6 -
10 | 3/31-4/6 |  |  |  | 0 - 1 - 3 - 6 -

## Matthew
Role: Quality Assurance Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 12.5 | 9 | 3.5 | 0 - Relearned Git, Watched Zach build both the django/react and react poc's, watched tutorials on both django and react 1 - plan future requirements 4 - discuss QA processes 5 - communication with team about project setup and my specific role 6 - set up Git/Git Desktop | 4 | 1 | 0.5 | 0 | 1 | 2 | 0.5 | 0 | establish group role, set up Github | unfamiliarity with django and react | rewatch poc builds, go through tutorials | continue learning framework, look into pivotal, learning QA roles | 6
2 | 2/3-2/9 | 8 | 6 | 2 | 0 - perform coding tutorials in both django and react/rewatch Zach's poc video 1 - explore pivotal, read up on pivotal 5 - begin SPPP doc / review lab 2 | 4 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | set up pivotal tracker, start SPPP | unfamiliarity with pivotal | read pivotal tutorials | add pivotal stories, finish SPPP, contribute to iter0 ppt | 12
3 | 2/10-2/16 | 16 | 11 | 5 | 0 - review tutorials on QA processing 1 - worked on adding stories to pivotal and finishing SPPP 5 - communication with group on pivotal/SPPP/iter0 ppt | 3 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | finish SPPP, finish iter0 ppt, finish pivotal stories | QA proccesses unfamiliarity | read up on QA development and implementation | assist in any technical work that may begin, try to get ahead of learning frameworks as the develop, learn more QA processes set up QA tracking | 10
4 | 2/17-2/23 | 12 | 10 | 2 | 0 - review tutorials on QA processing, review Zachs zoom recording on setting up OAuth with django/react 1 - reasses pivotal stories 5 - team meeting | 6 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | edit pivotal stories | react/django unfamiliarity | tutorials, zachs tech sessions on the environment | begin e2e testing analysis, learn selenium/pytest | 10
5 | 2/24-3/2 | 17 | 13 | 4 | 0 - selenium, pytest and other qa testing tutorials 4 - meet with George to begin qa end to end testing and requirement coverage sheets 5 - meeting with George/team meeting 6 - rewatch Zachs video on react | 6 | 0 | 0 | 0 | 1 | 4 | 2 | 0 | end-to-end testing spreadsheet, requirement testing coverage spreadsheet | running plan.ly locally, unfamiliarity with e2e testing rhetoric | tech sessions, tutorials, meet with george/zach | setup plan.ly locally, try to implement selenium | 12
6 | 3/3-3/9 | 22 | 16 | 6 | 0 - selenium tutorials, watching Zachs previous reacttech session, attending Zachs second react session 4 - fix end-to-end testing cases to remove OAuth 3 - implementation of Plan.ly on localhost, begin working to implement selenium 5 - meet with George, meet with Zach, Team meeting | 6 | 0 | 0 | 3 | 1 | 6 | 0 | 0 | begin setting up selenium, work on end-to-end testing spreadsheets | getting plan.ly to run locally, setting up selenium still not communitating to plan.ly | more tutorials, meet with others in group who have more experience, trouble shoot selenium | update e2e testing spreadsheets, get selenium working on plan.ly locally | 15
7 | 3/10-3/16 | 0 | 0
8 | 3/17-3/23 | 0 | 0
9 | 3/24-3/30 | 0 | 0
10 | 3/31-4/6 | 0 | 0
11 | 4/7-4/13 | 0 | 0
12 | 4/14-4/20 | 0 | 0
13 | 4/21-4/27 | 0 | 0
14 | 4/28-5/4 | 0 | 0

## Chris
Role: Requirements Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 6 | 4.5 | 1.5 | 0 - validated git connection and read up on/experimented with GitHub Desktop 2 - reviewed initial project conecpt per original documentation I created prior to this class beginning | 3 |  | 1.5
2 | 2/3-2/9 | 10 | 8 | 2 | 0 - learn Pivotal Tracker 6 - Joined POC call where Zach developed the foundational pieces of React/Django | 5 | [5 empty] | 3 |  | 1 - Created Pivotal tracker example stories
3 | 2/10-2/16 | 12.5 | 8 | 4.5 | 0 - Researching SPPP, Competitive/Related product analysis 7 - research similar products, added to SPPP, created competitor table | 3 | [6 empty] | 5 | 7 - SPPP related products segment |  |  | Integrate stories as a team, begin coding stories assigned, will have to learn about Django framework, python unit testing, and working in Python IDE.
4 | 2/17-2/23 | 10.5 | 6 | 4.5 | 0 - Learning about Figma and wireframing tools 2 - Wireframe in Figma 3 - Set up OAuth2 React/Python/Django with Zach | 1 |  | 2 | 3 |  |  |  |  | 5 - Communicated potential issues with Google OAuth login pattern as implemented, triggered a redirection of our login implementation | Some communication challenges around OAuth pattern based on my interpretation of documentation. |  | Work on wireframes and class diagrams.
5 | 2/24-3/2 | 8.5 | 6.5 | 2 | 0 - Learning Django/working in project to get it set up in environment 2 - Wireframes 2 - Class diagram 5 - reviewing hours and documentation | 4.5 |  | 1.5 |  |  | 0.5 |  |  | 2 - Create high level wireframes for user input | My wireframes could have been more comprehensive but did help open discussion around potential design. |  | Begin implementing user stories.
6 | 3/3-3/9 | 18.5 | 14.5 | 4 | 0 - Learning React & Django, meeting with Vibhu & Zah on using resources 3 - Committed code to github 6 - Setting up VS Code, Python, React on local machine | 8.5 |  |  | 3 |  |  | 3 |  | 3 - updated database with Event model based on class diagram in SDD. Added two API calls to get all events and get a specific event. Created an Event list in React and the fields and submit button to add a new event. | This was an extremly challenging week for me. Learning to work with Python in the VSCode environment caused a number of instances where depenedncies(due to user error) were not available. Learning the basics of react and then implementing code based on the existing structure was also challenging. The most challenging individual part was passing a parameter through the URL, to the router, then to the view. This is similar to Spring but has its own quirks. Additionally, I have never used our ORM, python migrations, ora remote NoSql database. | Most of the learning challenges have been overcome. | Finish user stories, complete API calls around events. Document code, componentize React Event segment. Pass the linter and make a pull request. | 12

## Aysha
Role: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 01/27-02/02 | 8 | 7 | 1 | Individual Task Breakdown 0 - Refreshed Git,Watched Zach tutorial on Django 5 - communicated with team members on my role 6 - set up git 7 - research on security related functions | 3 |  |  |  |  | 1 | 1 | 2 | 1. Completed Lab 1 | 1. No previous experience with Django 2. My individual contribution to the task not clear | 1. Talk with Karen to get in track 2. Work on my contributtion to the team | Meet Karen and discuss regarding Django and lab 1 | 6
2 | 03/02-9/02 | 9 | 8 | 1 | Individual Task Breakdown 0 - DJango, Rest API for Django 1 - Work on user stories 3 - Creater User stories and assigned points 5 - Communicated with Karen and worked on pending task | 4 | 1 |  | 1 |  | 2 |  |  | 1. Completed Lab 2 | 1. Need to work more on programming in Django 2. My individual contribution to the task is still a work in progress | 1. Talk with Karen to get in track 2. Work on my contributtion to the team | Meet Karen and discuss task progress and lab 2 | 7
3 | 02/10-02/17 | 17 | 12 | 5 | Individual Task Breakdown 0 - Research on non functional requirments 1 - Worked on user stories 3 - completed SPPP and presentation 5 - Communicated with Team and decided on the presentation | 2 | 2 |  | 3 |  | 5 |  |  | 1. Completed SPPP and presentation | 1. Worked on security protocols | None 2. Work on my contributtion to the team | Make sure lab2 is done properly,determine test and fix erros made previously | 10
4 | 02/17-02/23 | 11 | 8 | 3 | Individual Task Breakdown 0 - Zachs tutorial 1 - Security design for software system 2 - Communicate with Zach, decide security design | 3 | 2 |  |  |  | 3 |  |  |  | 1. need to work on security protocols | 1. Work with Zach regarding security design | Need determine proper OAuth workflow with front- and back-end | 10
5 | 2/24-3/2 | 15 | 10 | 5 | Individual Task Breakdown 0 - Zachs tutorial 1 - Research on OAuth 6 - Set up the working enivornment | 3 | 1 |  |  |  | 6 |  |  |  | 1. need to work on security protocols 2. need to setup working environment | 1. Discuss with Team on setting up the working environment | update the non-functional requirements OAuth security breach and find possible solutions Complete the presentation PPTX and finish the document sections | 15
6 | 3/3-3/9 | 19 | 13 | 6 | Individual Task Breakdown 0 - Zach Turotrial 1 - Completed ppt for group presentation,SDD dcouments and updatednon functional requirement 2 - security design analysis 5 - communication with Team members and decided on indvidual task 6 - setup working environment | 3 | 5 | 2 |  | 1 | 2 |  |  |  | 1. Waiting for confirmation from the Prof on Non functional requirement 2. Communicate with other team members regarding the security presentation | 1. Complete the ppt for security presentation | Complete the presentation PPTX for secuirty presentation | 17