## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 1/27 - 2/16 | Established norms for epics vs. labels in PivotalTracker Divvied up roles and responsibilities Decided tech stack Decided DevOps tools Decided hosting environment Established scope of initial project phase | None yet | Varying levels of technical expertise on the team, including with use of ReactJS and Django. Need to assign stories to developers based on story complexity. | Need to come up with clearer assignment of tasks and communication of team deadlines given varying schedules amongst engineers. | 0 | 35 in icebox for essential/desirable | 0 | 0 | 0 | 189.5 | 134 | 8 | 47.5 | 22 | 4 | 2 | 3 | 33.5 | 14.5 | 7.5
1 | 2/17 - 3/9 | Implemented initial UI using react-bootstrap User registration User login Basic CRUD operations on a record type in database End to end connectivity with database |  | Limited test coverage thus far |  | 0 | 10pts in current iteration, 7 pts just awaiting testing | 0 | 0 | 0 | 214.5 | 153 | 8 | 45 | 25 | 18 |  | 0.5 | 38 | 10.5 | 8
2 | 3/10 - 4/6 | Create/edit event Event component/detail page work started on invitee management Handful of bug fixes for auth/session management | Refactoring needed for dashboard and event pages | Need to whittle down remaining requirements to what is capable within semester Don't have clear standards for react implementation - props versus API calls? what consistutes its own component, etc. | Will incorporate a discussion of norms/best practices into next team meeting | 9 | From previous iteration: 2 remaining, plus several bugs which we don't estimate. Next iteration yet to be planned. | 9 | 4 | 5 | 389.75 | 310.25 | 79.5 | 63 | 27.5 | 22 | 64.25 | 43 | 39 | 40.5 | 11
3 | 4/7 - 4/28 | Task lists New UI Final work on invitee management | Had to refactor most components from using props to using fetch calls to populate themselves. | Meetings keep having to be rescheduled | N/A | 24 | No more | 3 | 2 | 3 | 381.5 | 308 | 73.5 | 54.5 | 27 | 19 | 79 | 48 | 41 | 30.5 | 11

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
George | Overview, Management Plan, Objectives & Priorities | Logged a handful of bugs, construct requirements for most "optional" features, close bugs/requirements once complete | Wireframe designs | Written narrative in many sections | Completed assigned section in each presentation | Handled most features related to invitee list management, initial UI design of event page, and ability to edit/delete event | Establish framework for managing system tests with tracking spreadsheets | Manage releases on GitHub and submissiones on Blackboard | Run all group meetings, follow-up on individual deliverables on Slack, oversee preparation of all documents
Aysha | Non functional Requirements,Completed Reference and Glossary section | Logged a bug,wrote two stories for invitee | Security and intended the document and central aligned it | Discussed the testing for Non Functional requirments | Completed secuirty presentation and assigned part for each Iteration | Worked with pair programming implemeted invitee application that able to invite,delete, change ownership of a invitee | Did manual testing on invitee application | I was able to setup the working environment, pull and push from github | Established a very efficicent communication team members,also did multiple meeting for pair programming
Karen | Functional requiremnts, fix style | Made the CRUD for event stories, add bug when detected | Component, class, use case and sequence diagram, fix style | N/A | Completed assigned section in each presentation, and create initial template | Worked with pair programming for the add invitee, send email, validation of invitee, delete an invitee user stories | Refactoring a feature about the event invitee. | I was able to understand and do a merge of a branch into another one (with confilcts), with George | Constant communication with my pair programming team. Attendance at established meetings.And constant questions if I did not know or if I felt lost.
Chris | The "related work" section. | Go To Event From Feed, View feed of events. | Reviewed document for issues/QA. | N/A, wrote a few tests that were used in the project. | I0: Pivotal I1: Architecture I2: User Story Overview I3: Requirements | Worked on viewing an event from the feed, converting dates between the UI and database and marking a task complete. | Wrote tests to check if an event had been created and if so was it in the feed, then deleted the event. Also wrote tests to check if a date was entered and if the validator worked. | Set up environment on local machine, committed code, make pull requests to dev and other branches. Not directly responsible for initial configuraiton. | Worked with team through regular meetings and Slack conversations to aid in highlevel decision making, communicate issues, and ask for help from experienced team members when necessary.
Zach | Configuration Management section | Logged some bugs, wrote authentication stories that I eventually built out | Contributed to Security section | N/A | Completed assigned section in each presentation, often handled the demos | Did a lot of the initial project setup, implemented most of the front end ui and redesign, created dashboard, homepage, navigation, sideNav, footer, authorization components, built out front end and back end authentication | Refactored the dashboard, navigation, event components as part of redesign | Set up initial configuraation and deployment to Heroku, connected database to project, responsible for continuous Heroku deployment and CI/CD pipeline | Worked with team through meetings and Slack messages, hosted workshops to get team memebers familiar with React and Django together, created a development readme to provide instructions on setting up local environment and provide guidelines for code
Matt | Quality Assurance Plan | Logged bugs, wrote descriptions, added testing | N/A |  | Completed assigned QA/Testing section in each presentation Iteration 2 included both system and unit testing demos | Wrote and refactored all selenium scripts for each iteration, helped refactor and edit the unit testing scripts as well with Vibhu, implemented the Htmltestrunner module to generate reports upon running system testing scripts, in the last iteration worked a lot with Zach and Vibhu working through bugs (refresh error, edit event errors etc.) and different implementation issues | initially worked with George to set up the requirements coverage spreadsheet as well as to begin the end to end test cases spreadsheet,wrote the selenium testing scripts, worked with Chris on a few of these scripts, spoke with Aysha about testing of nonfunctional requirements, refactored testing scripts after each iteration to fix any changing code, made sure to have full test coverage for each of the accepted stories, oversight of the unit testing and worked with Vibhu to refactor this and work through errors, also implemented auto generation of testing reports | Set up local environment, committed code, worked on multiple branches throughout, work with the direct herokuapp | Worked with team members throughout different meetings, attend the technical sessions to keep up to speed, pair program with multiple people to both teach selenium and testing implementaion as well as to learn and assist in working through issues
Vibhu | Overview, Management plan, documentation standard | Logged a bug, created CRUD user stories for to dolist, created user / owner differentiation story in to do list. | Database design using usecase and class diagrams. Modified some model design to make it efficient in our application. | N/A | iteration 0: Modified Scrum method, iteration 1: database design, classes and automatic api iteration 2: Lessons Learned iteration 3: implementation | Kind of like a jack of all trades 1. initially help chris set up event page 2. helped in major refactoring of dashboard, event page 3. converted static pages(only updates when refreshed) to dynamic(updates whenever anything is done without refresh). 4. set up backend methods (get / post / patch / delete) for most of the urls 5. Fixed bugs people were facing or when webapp started breaking. 6. Major refactoring to make every page load information separately rather than relying on parent component. | created unit tests for testing out model field validators and empty embedded object rejection. | set up working environment, helped people set up their environments, fix git conflicts, minor bugs everyone faced | Provided assistance in setting up meetings, working together with people when they were working on a feature, conducted technical workshops, explaining react and django concepts to someone if they were having problems.

## George
Lead Roles: Team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 7.5 | 6 | 1.5 | 0 - Learn PivotalTracker best practices 1 - plan high level requirements with team 2 - weigh SQL/noSQL approaches 4 - discuss best QA approach with team 5 - run team meetings, remind of deliverables 6 - work with Zach to establish DevOps policies with team | 1 | 1 | 0.5 | 0 | 1 | 2 | 0.5 | 0 | Established group communication standards, project scope, roles and responsibilities, housekeeping items | None yet | Need to incorporate Aysha to team as Security Leader and get her up to speed on project scope | Need to establish policy for branching | 3
2 | 2/3-2/9 | 6.5 | 4.5 | 2 | 0 - none 1 - Input a few test stories to Pivotal, solidify scope with team 2 - none 3 - none yet 4 - continue to discuss QA procedures with team 5 - run team meetings, start SPPP doc with team 6 - work with Zach to solidify DevOps practices | 0 | 0.5 | 0 | 0 | 0.5 | 3 | 0.5 | 0 | Start of SPPP | None yet | None yet | iter0 deliverables | 5
3 | 2/10-2/16 | 15.5 | 10.5 | 5 | 0 - none 1 - entered all "optional" requirements in Pivotal 2 - none 3 - none yet 4 - none yet 5 - ran meetings, worked on iter0 deliverables 6 - established CI/CD pipeline policies with Zach 7 - none | 0 | 2 | 0 | 0 | 0 | 8 | 0.5 | 0 | SPPP sections, iter0 PowerPoint slides | None yet | None yet | Divvy up stories for initial implementation, collaborate on design doc, refine Pivotal | 20
4 | 2/17-2/23 | 7 | 5 | 2 | 0 - long discussion of OAuth in weekly group meeting 1 - refined stories with group for week 1 of iteration 1, decided scope for upcoming week. 2 - Initial design discussion with Karen during weekly meeting 3 - none outside of disussion during weekly meeting 4 - none 5 - lead weekly group meeting, side discussions with all members 6 - none 7 - none | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | Updated meeting minutes, divvied up SDD document per section | Need to establish security mechanism front- vs back-end. | Aysha/Vibhu/Chris to determine architecture | Work with Matt on end-to-end test management. | 2
5 | 2/24-3/2 | 3 | 1 | 2 | 1 - reviewed stories on pivotal 5 - hosted team meeting | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
6 | 3/3-3/9 | 18 | 12 | 6 | 0 - rewatched Zach workshop from previous week, attended current workshop 1 - fixed pivotal stories to revert to django-managed auth 2 - built wireframes in whimsical 3 - none 4 - fixed test cases on Pivotal for switch away from google auth 5 - ran group meeting, updated deliverables 6 - set up local environment, worked on getting Selenium up and running 7 - none | 2 | 1 | 1 | 0 | 1 | 4 | 3 | 0 | Created wireframes, updated SPPP, proofread SDD, added intro slides to presentation, checked progress report for adherence to required formulas | Unable to get Selenium up and running yet | Work with Matt to resolve | Selenium up, first few automated tests written and working | 5
7 | 3/10-3/16 | 6 | 4 | 2 | 0 - reviewed online react tutorial regarding component state 1 - none 2 - designed events page using react-bootstrap 3 - built events page and included fontawesome icons 4 - none 5 - ran group meetings 6 - none 7 - none | 1 |  | 0.5 | 0.5 |  | 2 |  |  | Got fontawesome working and implemented layout of event page |  |  | Bring in state data to event page | 4
8 | 3/17-3/23 | 6 | 2 | 4 | 3 - continued work on events page |  |  |  | 2 | [7 empty] | Make new component for EventForm | 4
9 | 3/24-3/30 | 11.5 | 8 | 3.5 | 0 - lots of react tutorial reading online, esp during debugging 1 - added chores for certain implementation tasks 2 - conceived refactoring for reuse of event form for create vs. edit 3 - created new eventform component to be able to reuse in edit event page 4 - none 5 - ran group meetings 6 - none 7 - none | 3 | 0 | 1 | 1 | 0 | 3 | 0 | 0 | EventForm component, started work on edit event functionality | Need to make sure we are consistent in use of state amongst components | Confer with implementation leader | Finish ability to edit event
10 | 3/31-4/6 | 18 | 14.5 | 3.5 | 0 - reading of Stackoverflow posts, general debugging information 1 - added several bugs; closed stories that had been coded and not delivered 2 - designed Invitee as separate component to manage adding guests to event 3 - finish inforporation of event form, help Karen/Aysha with incorporating invitee 4 - create simulation test as part of lab 3 5 - run all team meetings, make sure everyone has an assignment to do for project presentation 6 - general git operations 7 - none | 0.5 | 0.5 | 1 | 8 | 1 | 3 | 0.5 | 0 | Invitee, EventForm component incorporation into the UI. A few methods in views.py to handle those parts of the UI. Updating requirements in Pivotal. | Major refactoring is required to get events populated based on invitee records, instead of creator's UserID | Vibhu taking lead for refactoring | Finish ability to add invitees to events; populate InviteeList from event object's participants array | 7
11 | 4/7-4/13 | 10 | 8 | 2 | 0 - better understanding of props, state. Reading of Django REST framework. 1 - None 2 - Redesign of Invitee component because of state issues. 3 - Invitee list - finish; invitee adder - continue working 4 - Manual testing on invitee management 5 - Run group meetings; send messages on Slack to check in on work 6 - None 7 - None | 1 | 0 | 1 | 3 | 1 | 2 | 0 | 0 | Invitee list - make it live and tied to database. Perform initial implementation on add invitee workflow. | Unable to re-render child component (Invitee List) so had to bring component into Event and not have it be a separate component. This is a brute force workaround... | Discuss with Zach - perhaps reload entire page | Finish invitee management. | 2
12 | 4/14-4/20 | 9 | 7 | 2 | 0 - None 1 - None 2 - Design interaction between invitee and invitee list components 3 - Make it so invitee list updates when new people are added 4 - None 5 - group meetings 6 - Clean up branches I had been working on; merge 7 - None | 0 | 0 | 1 | 3 | 0 | 2 | 1 | 0 | Finish most behavior with invitee list management, esp. regarding add new invitee. | Unclean/inconsistent data in the database is breaking the UI. | All users update to the latest dev branch since this addresses the issue with dates being saved as strings and breaking the UI. | Add toggle button for users/co-owners | 5
13 | 4/21-4/27 | 18 | 10 | 8 | 0 - Learn react best practices for updating state arrays 1 - None 2 - None 3 - Add toggle invitee status, uninvite, and redo event page for owner/non-owner permissions 4 - Manual testing of invitee list behavior 5 - Group meeting management 6 - General GIT cleanup/management 7 - None | 1 | 0 | 0 | 5 | 1 | 2 | 1 | 0 | Add ability to change invitee to co-owner, uninvite an invitee, and refactor event page to hide "Edit" and invitee management buttons for users who aren't co-owners | Page is slow to update after new invitee is added. Perhaps a status bar/progress indicator would help UI/UX. | Unsure how we can solve this given time left for semester. | N/A | N/A

## Vibhu
Lead Roles: Backup Team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 6.5 | 5 | 1.5 | 0 - Revisit basics of Django, React 2 - Researched and Suggested the pros of using noSQL over SQL based db 4 - Discussed inclusion of Basic unit tests for checking backend Featues 5 - Help inorganizing meetings, setting up agenda, provide an expert opinion | 2 | 0 | 0.5 | 0 | 0.5 | 2 | 0 | 0 | set up git, formalized the working of project, selected tech stack. | None | None | research on deploying frontend-backend combined | 2
2 | 2/3-2/9 | 7 | 5 | 2 | 1 - Researched and discussed use of docker for unifying build process. 2 - Explored more on the development of MVP and functionalities of the product 5 - Basic logistic stuff and setting up meetings | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 0 | Create an in-depth product functionality doc, work on SPPP document | None | None | Set up pivotal tracker, iter 0 deliverables | 2
3 | 2/10-2/16 | 8.5 | 4.5 | 4 | 0 - Learnt basics of Pivotal tracker 1 - Filled out user stories for pivotal tracker and completed deliverables for iter - 0 3 - Researched on setting up standards for documentation, code-style, pull-request and bugs 5 - Assisted in meetings and basic check-up | 0.5 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | set up github and code standards, Pivotal tracker, iter-0 presentation | None | None | work on wireframes, start implementing functionality, Learn more about unit-tests | 5
4 | 2/17 - 2/23 | 6.5 | 4.5 | 2 | 0 - Learnt about docker, discussion about oAuth. 1 - Added user acceptance tests and modified stories on pivotal tracker. 2 - Set up Class diagrams for my user stories. 5 - Assisted in weekly meetings. | 1.5 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | None | None | None | Zack is supposed to do majority of the work so just checking up with the group | 1
5 | 2/24 - 3/2 | 5 | 3 | 2 | 0 - Setup repository environment and test login/signup 1 - know more about DB and Classes section of SDD 5 - Basic Meeting logistics | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Setup app environment, thought about DB classes and the functions for user story. | None | None | Set up automatic API, Work with chris to create this week's user stories, Learn django-rest-framework. | 6
6 | 3/3 - 3/9 | 13 | 8.5 | 4.5 | 0 - Learnt about react.js, django-rest-framework, djongo. 1 - Set up automatic API for front end and backend and completed deliverables for iteration-1 2 - Used Karen's diagrams to construct database models. 3- Pair programming with chris to help him setup the event class 5- Assisted in daily meetings, organized logistics. | 2 | 2 | 1 | 2 | 0 | 1.5 | 0 | 0 | Added jsdoc support to document code in frontend, completed SDD document, Iteration-1 presentation | None | None | Help with anything chris or zack need completion in. Add pdoc documentation code for python backend. | 3
7 | 03/10 - 03/16 | 12.5 | 8.5 | 4 | 0 - Read up on different fields in Mongo, how they link up with django and learn more about embedded fields vs reference fields 2 - Made some changes to the database model with the group (storing embedded models too) and added data validators. 5 - Created a helpbook for mongo queries in django to help the group and organized group meetings. | 3 | 0 | 4 | 0 | 0 | 1.5 | 0 | 0 | Completed DB classes in django to be used in other components | None | None | work on completing event page | 5
8 | 03/17- 03/23 | 9 | 7 | 2 | 0 - Read up on component life cycle in react.js, states and how projects are organized and how viewset are updated in django. 1- Reworked the dashboard component to display all the events a user is owner for, added a modal for creating a new event dynamically. 5- Assisted in organizing weekly meetings. Conducted weekly technical session on using mongodb queries in python. | 2 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | Worked on the dashboard component, eventCreation Form and Event page and linked backend methods (post request, get all, get specific) | None | None | Work on unit testing model components | 3
9 | 03/24-03/30 | 8.5 | 5 | 3.5 | 4 - Constructed automated unit tests for Database models 5 - Weekly Meetings + weekly technical session on react + django integration + solved bugs of every group member. | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | None | None | None | Just helping everyone with refactoring
10 | 03/31-04/06 | 7.5 | 5 | 2.5 | 3 - Refactored dashboard component to display host names, fixed bugs in display event section to show all events a user is participant of rather than just host. 5 - Weekly Meeting + helping george with refactoring event and eventform component + solve group queries. 7 - Prepare presentation for iteration 2 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | Refactoring components + fixing bugs + iteration 2 presentation | None | None | Adding to-do lists, functionality for inviting users to the event. | 5

## Karen
Role | Requirement and design leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 01/27-02/02 | 7.5 | 6 | 1.5 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Set up git, commit a test message on git | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 03/02-9/02 | 7 | 5 | 2 | 0 - learn django, read several tutorials 1 - create user stories 5 - review lab2 and iteration#0 6 - set up django | 1.5 | 1.5 |  |  |  | 1.5 | 0.5 |  | None | 1. Need to keep working with django and react | 5- Some points arent very clear, emailed the professor | Continue to learn Django and define requirements and tasks Reasearch about design and review the tutorial made by Zach Finish section in SPP and lab2 | 8
3 | 02/10-02/17 | 12 | 7 | 5 | 0 - Learn Pivotaltracker 1 - Enter the user stories related to managing a private event 5 - Finish section in SPP and lab2 | 0.5 | 3 |  |  |  | 3.5 |  |  | Section of functional requiremnts( SPP docuemnt and presentation), and style of the document | None | None | Review design patterns and start with SDD document, assist in any technical work that may begin | 8
4 | 2/17-2/23 | 9.5 | 7 | 2.5 | 0 - Learn modeling React class 2 - software architecture and class diagram SDD | 3 |  | 4 | [5 empty] | Software architure , and part of class diagram | Definition of some classes | Review with team , we all found the solution | Fix and finish sections, set up project in my computer | 8
5 | 2/24-3/2 | 7 | 5 | 2 | 2 - changes in the diagrams 6- set all configuratio |  |  | 3 |  |  |  | 2 |  | Software architure, class diagram and patterns | None | None
6 | 3/3-3/9 | 11 | 5 | 6 | 0 - rewatched Zach workshop from previous week 2 - set pptx slides and orginize SDD section document | 2 |  |  |  | 3 |  |  |  | Software architure, class diagram and patterns | None | None | Start developing some stories and star reviewn the next deliverable. | 6
7 | 3/10-3/16 | 10 | 8 | 2 | 0 - setting up all the things we needed and find suitable solution for requirement | [6 empty] | 8 |  | None | None |  | keep coding the story | 9
8 | 3/17-3/23 | 17 | 13 | 4 | 0 - investigation ways to achieve the front end part of user story assigned 5 - pair programming with Aysha 6 - implementing story : add event invitee | 4 | [5 empty] | 9 |  | Part of functionality for story | None |  | keep coding the story | 8
9 | 3/24-3/30 | 14.5 | 11 | 3.5 | 0 - selenium 2- changes from component and class design 3 - pair programming with Aysha 6 - implementing story : add event invitee | 3 |  |  | 5 |  |  | 3 |  | Part of functionality for story | Lack of knowledge in security infromation | sit with George and review the code, and do some refactoring on it | keep coding the story | 8
10 | 3/31-4/6 | 19.5 | 14 | 5.5 | 0 - selenium 3 - pair programming with Aysha and refactoring with George 6 - finishing up story / refactoring | 3 |  |  | 6 |  |  | 5 |  | Functionality and changes in diagrams , version 2 of SDD | None |  | Test final code | 8
11 | 4/7-4/13 | 6 | 4 | 2 | 3 - pair programming with George and Aysha on Invitee list - finish and continue working on invitee adder 4 - Manual testing on invitee management |  |  |  | 3 | 1 |  |  |  | Invitee list tied to database. | None | None | Keep working on invite an invitee | 4
12 | 4/14-4/20 | 5 | 3 | 2 | 3 - pair programming with George and Aysha on make invitee list updates when new people are added |  |  |  | 3 |  |  |  |  | Finish most behavior with invitee list management | None | None | Finishing up like togglers by validating email | 5
13 | 4/21-4/27 | 14 | 6 | 8 | 2 - Creating User cases and sequence diagram 3 - pair programming with George and Aysha on add toggle invitee status, uninvite, and redo event page for owner/non-owner permissions |  |  | 3 | 3 |  |  |  |  | Add ability to change invitee to co-owner, uninvite an invitee, and refactor event page to hide "Edit" and invitee management buttons for users who aren't co-owners. Use cases diagram and description of only 2cases. Sequence diagram of the same 2 use cases. | None | None | None | None

## Matthew
Role: Quality Assurance Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 12.5 | 9 | 3.5 | 0 - Relearned Git, Watched Zach build both the django/react and react poc's, watched tutorials on both django and react 1 - plan future requirements 4 - discuss QA processes 5 - communication with team about project setup and my specific role 6 - set up Git/Git Desktop | 4 | 1 | 0.5 | 0 | 1 | 2 | 0.5 | 0 | establish group role, set up Github | unfamiliarity with django and react | rewatch poc builds, go through tutorials | continue learning framework, look into pivotal, learning QA roles | 6
2 | 2/3-2/9 | 8 | 6 | 2 | 0 - perform coding tutorials in both django and react/rewatch Zach's poc video 1 - explore pivotal, read up on pivotal 5 - begin SPPP doc / review lab 2 | 4 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | set up pivotal tracker, start SPPP | unfamiliarity with pivotal | read pivotal tutorials | add pivotal stories, finish SPPP, contribute to iter0 ppt | 12
3 | 2/10-2/16 | 16 | 11 | 5 | 0 - review tutorials on QA processing 1 - worked on adding stories to pivotal and finishing SPPP 5 - communication with group on pivotal/SPPP/iter0 ppt | 3 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | finish SPPP, finish iter0 ppt, finish pivotal stories | QA proccesses unfamiliarity | read up on QA development and implementation | assist in any technical work that may begin, try to get ahead of learning frameworks as the develop, learn more QA processes set up QA tracking | 10
4 | 2/17-2/23 | 12 | 10 | 2 | 0 - review tutorials on QA processing, review Zachs zoom recording on setting up OAuth with django/react 1 - reasses pivotal stories 5 - team meeting | 6 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | edit pivotal stories | react/django unfamiliarity | tutorials, zachs tech sessions on the environment | begin e2e testing analysis, learn selenium/pytest | 10
5 | 2/24-3/2 | 17 | 13 | 4 | 0 - selenium, pytest and other qa testing tutorials 4 - meet with George to begin qa end to end testing and requirement coverage sheets 5 - meeting with George/team meeting 6 - rewatch Zachs video on react | 6 | 0 | 0 | 0 | 1 | 4 | 2 | 0 | end-to-end testing spreadsheet, requirement testing coverage spreadsheet | running plan.ly locally, unfamiliarity with e2e testing rhetoric | tech sessions, tutorials, meet with george/zach | setup plan.ly locally, try to implement selenium | 12
6 | 3/3-3/9 | 22 | 16 | 6 | 0 - selenium tutorials, watching Zachs previous react tech session, attending Zachs second react session 4 - fix end-to-end testing cases to remove OAuth 3 - implementation of Plan.ly on localhost, begin working to implement selenium 5 - meet with George, meet with Zach, Team meeting | 6 | 0 | 0 | 3 | 1 | 6 | 0 | 0 | begin setting up selenium, work on end-to-end testing spreadsheets | getting plan.ly to run locally, setting up selenium still not communitating to plan.ly | more tutorials, meet with others in group who have more experience, trouble shoot selenium | update e2e testing spreadsheets, get selenium working on plan.ly locally | 15
7 | 3/10-3/16 | 10 | 10 |  | Individual Task Breakdown 0 - Selenium tutorials 4 - Integrate selenium test code into a feature branch in Git 5 - Communicate with Zach about errors | 4 | 0 | 0 | 0 | 5 | 1 | 0 | 0 | begin implementing selenium to run the automated tests and set up the testing branch on github | getting through multiple errors with setting up selenium | worked through the errors with Zach and got selenium running in my environment | clean up and finish automated testing scripts and help others begin working with selenium | 12
8 | 3/17-3/23 | 9 | 9 |  | Individual Task Breakdown 0 - Automated testing tutorials and documentation 4 - Refactoring Selenium testing 5 - Help Chris set up selenium and begin working on automated testing for the event creation | 3 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | refactor testing scripts and helped chris begin working on also using selenium | errors with setting up selenium | worked through the errors with Chris and got him running selenium | give tech session about selenium script writing and also show a demo of what is running currently on testing branch | 12
9 | 3/24-3/30 | 15 | 15 |  | Individual Task Breakdown 0 - Tech session including Vibhus discussion on unit testing and group discussion on Git 1 - Refamiliarize with the e2e testing sheet as well as the requirement coverage sheet and pivotal status 4 - Fix testing scripts and work through multiple errors, give selenium demos and discussion of how the scripts work 5 - Work on event testing with Chris 6 - Merge dev branch into testing so that the most up to date features can be tested | 2 | 2 | 0 | 0 | 7 | 2 | 2 | 0 | clean up end to end testing sheet as well as requirement coverage sheet, update testing branch by having dev merged into it, fix testing scripts | some errors with selenium scripting | work through finding different elements and how to test them | work on generating reports automatically for the selenium scripts, have dev merged into testing branch to make most up to date | 20
10 | 3/31-4/6 | 27 | 27 |  | Individual Task Breakdown 0 - Read documentation on Git, Selenium, Errors, Pytest, HTMLTestRunner 1 - Update End-to-End Testing, Requirement Analysis, and Testing Metrics sheets 2 - Fill out the new Testing documentation 3 - Implement HTMLTestRunner to generate reports for the automated testing scripts 4 - Refactor Selenium test cases, work through multiple errors when running the test scripts (pylint error, eslint error, module not found error, arrtibute not found error etc), get testing to run also on the herokuapp site version and not just localhost 5 - Talk with Chris, Vibhu, Zach about different errors 6 - Merge dev into feature/testing branch and make up to date | 5 | 2 | 1 | 10 | 2 | 5 | 2 | 0 | created report generation for the new cleaned up testing scripts, testing branch completely up to date with dev branch as of 4/5, all testing sheets (e2e, requirement coverage, testing) up to date as of 4/5 as well | lots of issues setting up the report generation (pylint error, eslint error, merging errors, npm errors, permission denied errors, module not found errors, attribute errors, webdriver errors) | all issues fixed or worked around: (pylint error: fixed in the package.json file, eslint error: no longer occurs upon recloning repository, merging errors: had to delete all files and recolon the repository, npm errors: had to reinstall multiple packages and use npm install --force, permission denied errors: still not fixed, module not found errors: fixed from package.json update, attribute errors, webdriver errors: needed to use full path and not just relative) | readjust the file structure for the automated testing, look into changing the structure of the reports, merge into dev, look into integrating unit testing into report generation | 15
11 | 4/7-4/13 | 11.5 | 9.5 | 2 | Individual Task Breakdown 0 - Read documentation on Git, Selenium, Errors, Pytest, HTMLTestRunner 1 - Update End-to-End Testing, Requirement Analysis, and Testing Metrics sheets 4 - Refactor Selenium test cases as we merge in new features | 3 | 0.5 | 0 | 0 | 6 | 0 | 0 | 0 | created report generation for the new cleaned up testing scripts, testing branch completely up to date with dev branch | clean up report generation errors | as the reports capture errors work through the scripts to fix the automated testing | continue to work on refactoring testing scripts as new features are implemented | 12
12 | 4/14-4/20 | 11.5 | 9.5 | 2 | Individual Task Breakdown 0 - Read documentation on Git, Selenium, Errors, Pytest, HTMLTestRunner 1 - Update End-to-End Testing, Requirement Analysis, and Testing Metrics sheets 4 - Refactor Selenium test cases as we merge in new features | 3 | 0.5 | 0 | 0 | 6 | 0 | 0 | 0 | created report generation for the new cleaned up testing scripts, testing branch completely up to date with dev branch | clean up report generation errors | as the reports capture errors work through the scripts to fix the automated testing | continue to work on refactoring testing scripts as new features are implemented | 12
13 | 4/21-4/27 | 31 | 21 | 10 | Individual Task Breakdown 0 - Read documentation on Git, Selenium, Errors, Pytest, HTMLTestRunner 1 - Update End-to-End Testing, Requirement Analysis, and Testing Metrics sheets 4 - Refactor Selenium test cases as we merge in new features 5 - Work with Vibhu, Zach about different errors and merging together the final code 6 - Merge dev, dashboard, design and todo branches into feature/testing branch | 2 | 2 | 0 | 0 | 12 | 4 | 1 | 0 | continued to generate reports for testing, fully updated the e2e test case sheet as well as the requirement coverage sheet, made sure to have full testing for all accepted pivotal stories, work on merging all of the final features and make sure the webapp runs correctly, work through multiple errors with Zach and Vibhu to finalize the webapp, work on final merges in Git | tons of issues while merging final features, a big UI update that overhauled the site in the final week that broken all testing and forced all testing scripts to be refactored slightly as xpaths began to break, some features also began to break as we worked on those final features and fixing final bugs

## Zach
Role: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 9.5 | 6 | 3.5 | 0 - learn to connect react and django together 6 - create two proof of concepts, one using React/Django, one using Django 7 - Zoom call with Chris and Matt so they can watch how the POC setup works | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 0 (2) | Created two pocs so group could decide on tech stack | N/A |  | Setting up CI in Github | 6
2 | 2/3-2/9 | 8 | 6 | 2 | 0 - learn Github Actions and CI/CD, research best actions to use 6 - Implement Github actions for CI 7- workshop: log in with google | 3 | 0 | 0 | 0 | 0 | 0 | 3 |  | Started work on SPPP | N/A |  | Deploying to Heroku, working on SPPP | 6
3 | 2/10-2/16 | 12 | 7 | 5 | 0 - learn how to deploy django/react projects to Heroku 1 - work on SPPP and Pivotal Tracker 6 - set up main to depoy to Heroku, | 3 | 2 | 0 | 0 | 0 | 0 | 2 |  | Worked on SPPP and Pivotal Tracker requirements | N/A |  | Adding linters to CI process, documenting development branch, setting up Mongo, wireframes | 15
4 | 2/17-2/23 | 20 | 18 | 2 | 0 - learn how to use google ouath 3 - work on log in, sign up stories 6 - reconfigure local django database 7 -workshop: log in with google | 4 | 0 | 0 | 10 | 0 | 0 | 1 | 3 | Setup oauth and user log in and sign up | N/A
5 | 2/24-3/2 | 23 | 21 | 2 | 0 - learn how to connect mongodb to django backend 1 - work on security analysis on SDD 3 - work on log in, sign up stories 6 - switch project database to MongoDb 7 - workshop: react overview | 2 | 0 | 0 | 14 | 0 | 0 | 3 | 2 | Switched database to mongodb, set up development heroku server | Ouath proving difficult to manage
6 | 3/3-3/9 | 19 | 14 | 5 | 0 - learn how to implement jwt with django 1 - SDD work 3 - redo authentication and log/logout stories, added preliminary ui/ux 6 - workshop: react overview part 2 | 3 | 1 | 0 | 8 | 0 | 0 | 0 | 2 | -Reconfigured app authentication to use jwt and django's built in User model -Implemented ui design from wireframes to available components | N/A |  | Work on CRUD for Events and tying them to users | 15
7 | 3/10-3/16 | 4 | 2 | 2 | 6 - merged event pull request to dev branch, | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | -merged new event features into development branch
8 | 3/17-3/23 | 4 | 0 | 4 | 5 - 1 - 3 - 6 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 3/24-3/30 | 5.5 | 2 | 3.5 | 3 - approved pull requests for event page to be merged into dev | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | -merged new event features into development branch and msde sure they were working |  |  | -fixing login errors and session length | 5
10 | 3/31-4/6 | 13.5 | 10 | 3.5 | 5 - Met with George, Matt, Chris to trouble shoot different bugs 4 - created some tests for lab 3 3 - worked on session implementation, error handling for login 6 - push deployment and main branches to heroku for iteraiton 2 | 0 | 0 | 0 | 5 | 0 | 0 | 5 |  | -Extended jwt expiration length so user sessions last 24 hours isntead of 5 minutes -users now receive "incorrect username/password" when entering incorrect credentials -rolled back development branch to previous commits to fix a couple of errors with date validation | Could not create new users |  | -ui (css) updates and fixes -bug fixing cannot create new user | 15
11 | 4/7-4/13 | 3 | 1 | 2 | 3 - bug fixing 5 - group meetings | 0 |  |  | 1 | 0 | 2 | 0 | 0 | -bug fixes | N/A |  | -css updates and bug fixes | 10
12 | 4/14-4/20 | 3 | 1 | 2 | 3 - bug fixing 5 - group meetings | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | -bug fixes |  |  | -redesign app ui and cleaned up css -implement any new features into the new design | 30
13 | 4/21-4/27 | 57 | 49 | 8 | 3 - working on wholesale ui and css changes, implementating new features into new design 5 - meeting up to finalize presentation and project 6- fixing heroku bug 7 - design and wireframe work for new ui updates | 0 | 0 | 0 | 33 | 0 | 8 | 4 | 4 | -redesigned app ui and cleaned up css -implemented Vibhu's new features into the new design -heavily refactored React components | Deployment to Heroku caused issues

## Chris
Role: Requirements Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27-2/2 | 6 | 4.5 | 1.5 | 0 - validated git connection and read up on/experimented with GitHub Desktop 2 - reviewed initial project conecpt per original documentation I created prior to this class beginning | 3 |  | 1.5
2 | 2/3-2/9 | 10 | 8 | 2 | 0 - learn Pivotal Tracker 6 - Joined POC call where Zach developed the foundational pieces of React/Django | 5 | [5 empty] | 3 |  | 1 - Created Pivotal tracker example stories
3 | 2/10-2/16 | 12.5 | 8 | 4.5 | 0 - Researching SPPP, Competitive/Related product analysis 7 - research similar products, added to SPPP, created competitor table | 3 | [6 empty] | 5 | 7 - SPPP related products segment |  |  | Integrate stories as a team, begin coding stories assigned, will have to learn about Django framework, python unit testing, and working in Python IDE.
4 | 2/17-2/23 | 10.5 | 6 | 4.5 | 0 - Learning about Figma and wireframing tools 2 - Wireframe in Figma 3 - Set up OAuth2 React/Python/Django with Zach | 1 |  | 2 | 3 |  |  |  |  | 5 - Communicated potential issues with Google OAuth login pattern as implemented, triggered a redirection of our login implementation | Some communication challenges around OAuth pattern based on my interpretation of documentation. |  | Work on wireframes and class diagrams.
5 | 2/24-3/2 | 8.5 | 6.5 | 2 | 0 - Learning Django/working in project to get it set up in environment 2 - Wireframes 2 - Class diagram 5 - reviewing hours and documentation | 4.5 |  | 1.5 |  |  | 0.5 |  |  | 2 - Create high level wireframes for user input | My wireframes could have been more comprehensive but did help open discussion around potential design. |  | Begin implementing user stories.
6 | 3/3-3/9 | 18.5 | 14.5 | 4 | 0 - Learning React & Django, meeting with Vibhu & Zah on using resources 3 - Committed code to github 6 - Setting up VS Code, Python, React on local machine | 8.5 |  |  | 3 |  |  | 3 |  | 3 - updated database with Event model based on class diagram in SDD. Added two API calls to get all events and get a specific event. Created an Event list in React and the fields and submit button to add a new event. | This was an extremly challenging week for me. Learning to work with Python in the VSCode environment caused a number of instances where depenedncies(due to user error) were not available. Learning the basics of react and then implementing code based on the existing structure was also challenging. The most challenging individual part was passing a parameter through the URL, to the router, then to the view. This is similar to Spring but has its own quirks. Additionally, I have never used our ORM, python migrations, ora remote NoSql database. | Most of the learning challenges have been overcome. | Finish user stories, complete API calls around events. Document code, componentize React Event segment. Pass the linter and make a pull request. | 12
7 | 3/10-3/16 | 8.5 | 6.5 | 2 | 0 - Learning unit tests in Python/Django, GitHub desktop, Anaconda env Vs VS Code env, TDD 3 - Cleaning up code to update Pull request 5 - Slack | 3 |  |  | 3 |  | 0.5 |  |  | We are redirecting efforts between team members, learning testing is my new goal. The next two weeks will likely be more learning focused as other team members contribute to the code and round out various pieces of the project. | We have yet to complete a full dev cycle and have not implemented testing processess. | Other team members are going to be workign on contributing to the code base. At that point we will be in a good place to implementing testing and have a strong baseline to start working in true cycles from story to implementation to test and acceptance. | Learn more about slenium and unit tests. Think about refactoring opportunities. | 12
8 | 3/17-3/23 | 10.5 | 6.5 | 4 | 0 - Learning how models work in Python/Djongo 3 - Reviewing event creation code | 3.5 |  |  | 3
9 | 3/24-3/30 | 12 | 10 | 2 | 0 - Learning how selenium works 3 - Setting up selenium on project 4 - Writing Selenium/unit tests 5 - Planning | 2 |  |  | 2.5 | 5 | 0.5 |  |  | - Basic strategy for unit tests representing creating an event and checking its contents via selenium | - I have liited experience with Python, Python unit tests, and Selenium | - Continue to learn
10 | 3/31-4/6 | 17.75 | 15.25 | 2.5 | 0 - Learning python unit testing, Selenium, and React 1 - Reviewing Pivotal stories due 3 - Writing date validations for user entry 4 - Writing unit tests and Selenium tests 5 - Organizing/planning | 4 | 1 |  | 5.75 | 4 | 0.5 |  |  | - Selenium based unit tests for creating an event, checking event information was added - Validator for date inputs - Reviewed Pivotal tracker to help manage process and identify areas that need attention - Refactored validation code out of create/edit event function |  | - Keep writing tests to validate workflow and new/refactored code | - Contribute supporiting functionality to core user stories being implemented by other users - Writie more end to end Selenium tests | 10
11 | 4/7-4/13 | 7.25 | 5.25 | 2 | 0 - Learning about date objects and converting/parsing 3 - Implementing date converters into code 5 - Practicing presentation | 1.5 |  |  | 2.75 |  | 1 |  |  | - Added date converters in areas that needed it such as the update client code as they were being sent to Mongo in the wrong format
12 | 4/14-4/20 | 6.5 | 4.5 | 2 | 0 - learned more about the linter and PR process 3 - cleared linter errors from pull request 5 - admin and planning | 2 |  |  | 2 |  | 0.5 |  |  | cleared linter errors on existing pull request
13 | 4/21-4/7 | 20.25 | 14.75 | 5.5 | 0 - Learning React/Mongo 3 - Implementing the call to the database to complete a task 5 - Organizing/planning 7- Reviewing team documents | 9 |  |  | 3.25 |  | 0.5 |  | 2 | - added complete flag for tasks to server that updated one of the Mongo locations where the flag was stored | Learned and relearn many things about react and mongo including: How to pass state in react, how components work, HTTP verbs, passing data between React via http to Django views using a PK and data within the HTTP request, how views and routing work, how mongo works between an auto generated id field, an _id field and the ObjectId field, how mongo object nesting works and how to unpackage/change them, how mongo get one/many, set one/many works. These all ended up being substantial hurdles that I did not originally anticipate.

## Aysha
Role: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 01/27-02/02 | 8 | 7 | 1 | Individual Task Breakdown 0 - Refreshed Git,Watched Zach tutorial on Django 5 - communicated with team members on my role 6 - set up git 7 - research on security related functions | 3 |  |  |  |  | 1 | 1 | 2 | 1. Completed Lab 1 | 1. No previous experience with Django 2. My individual contribution to the task not clear | 1. Talk with Karen to get in track 2. Work on my contributtion to the team | Meet Karen and discuss regarding Django and lab 1 | 6
2 | 03/02-9/02 | 9 | 8 | 1 | Individual Task Breakdown 0 - DJango, Rest API for Django 1 - Work on user stories 3 - Creater User stories and assigned points 5 - Communicated with Karen and worked on pending task | 4 | 1 |  | 1 |  | 2 |  |  | 1. Completed Lab 2 | 1. Need to work more on programming in Django 2. My individual contribution to the task is still a work in progress | 1. Talk with Karen to get in track 2. Work on my contributtion to the team | Meet Karen and discuss task progress and lab 2 | 7
3 | 02/10-02/17 | 17 | 12 | 5 | Individual Task Breakdown 0 - Research on non functional requirments 1 - Worked on user stories 3 - completed SPPP and presentation 5 - Communicated with Team and decided on the presentation | 2 | 2 |  | 3 |  | 5 |  |  | 1. Completed SPPP and presentation | 1. Worked on security protocols | None 2. Work on my contributtion to the team | Make sure lab2 is done properly,determine test and fix erros made previously | 10
4 | 02/17-02/23 | 11 | 8 | 3 | Individual Task Breakdown 0 - Zachs tutorial 1 - Security design for software system 2 - Communicate with Zach, decide security design | 3 | 2 |  |  |  | 3 |  |  |  | 1. need to work on security protocols | 1. Work with Zach regarding security design | Need determine proper OAuth workflow with front- and back-end | 10
5 | 2/24-3/2 | 15 | 10 | 5 | Individual Task Breakdown 0 - Zachs tutorial 1 - Research on OAuth 6 - Set up the working enivornment | 3 | 1 |  |  |  | 6 |  |  |  | 1. need to work on security protocols 2. need to setup working environment | 1. Discuss with Team on setting up the working environment | update the non-functional requirements OAuth security breach and find possible solutions Complete the presentation PPTX and finish the document sections | 15
6 | 3/3-3/9 | 19 | 13 | 6 | Individual Task Breakdown 0 - Zach Turotrial 1 - Completed ppt for group presentation,SDD dcouments and updatednon functional requirement 2 - security design analysis 5 - communication with Team members and decided on indvidual task 6 - setup working environment | 3 | 5 | 2 |  | 1 | 2 |  |  |  | 1. Waiting for confirmation from the Prof on Non functional requirement 2. Communicate with other team members regarding the security presentation | 1. Complete the ppt for security presentation | Complete the presentation PPTX for secuirty presentation | 17
7 | 3/10-3/16 | 9 | 5 | 4 | Individual Task Breakdown 0 - rewatched zach tutorial 1 - analysed the requirement of the invitee story | 4 | 1 | [6 empty] | Finilase invitee design | 1.Finalise design | 1. Do peer programming with Karen | Do zoom call with Karen and discuss the plan for next week | 30
8 | 3/17-3/23 | 41 | 37 | 4 | Individual Task Breakdown 0 - React,MongoDB 1 - work on invite stories 2 - design application that invite user 5 - peerprogramming with Karen 6 - setting up required packages for the invitee application | 10 | 14 | 2 |  |  | 10 | 1 |  | Worked on Invitee essential stories | 1.Waiting for professor response regarding the testing for non functional requirement 2.More research on React. 3.Need to learn how to sent email invitation through react | 1.Watch youtube videos on React | Work with Karen on improving the current application and find a way to sent invite | 60
9 | 3/24-3/30 | 40 | 36 | 4 | Individual Task Breakdown 0 - selenium 1 - lab 3 2 - improving invite design 3 - intial invite application 4 - did testing on selenium 5 - peer programming with Karen 6 - setting up selenium 7 - imporve last weeks work | 2 | 3 | 3 | 10 | 2 | 5 | 1 | 10 | Tested Additems() on selenium. Improved on last weeks work | 1.Lot of useless coding 2.Invite button issue | 1.Refractor the code | Complete the work and prepare for presentation | 40
10 | 3/31-4/6 | 29 | 23 | 6 | Individual Task Breakdown 0 - nodemailer 3 - Completed invitee application 5 - peer programming with Karen,talked with george regarding reviewing the code, talked with mac regarding testing for non functional requirements 7 - Added a bug in pivotaltrackor regarding the invitee application | 2 | 0 | 10 |  | 10 |  |  | 1 | Completed invitee application | 1. To add invited members in a table | 1.Collabrate with Karen and George regarding it | Try adding members iinvited to the webpage | 40
11 | 4/7-4/13 | 14 | 12 | 2 | Individual Task Breakdown 3 - pair programming with Karen and George did testing on invitee application 4 - tested inviting people | 0 | 0 | 0 | 10 | 2 | 0 | 0 | 0 | Check if the invited people exist in the database | 1.Unable to display invited people | Discuss with the team | Display invited people | 10
12 | 4/14-4/20 | 12 | 10 | 2 | Individual Task Breakdown 3 - pair programming with George and Karen on displaying invitee list and removing the invited people |  |  |  | 10 |  |  |  |  | major portion of the invitee is done | None | None | Refractoring and Completing the task | 5
13 | 4/21-4/27 | 15 | 7 | 8 | Individual Task Breakdown 0 - Use case 3 - pair programming with George and refracting the invitee page | 2 |  | 0 | 5 |  |  |  |  | Added functionality like invitee,uninvitee, make co owner, and hide co owner button for the rest | None | None | None | None